## Tasks
ID | Phase | Task | Why it matters | Owner | Depends on | Priority | Status | Source doc | Notes
T001 | 1. Foundation | Create a new Facebook account (alishbakamran12345@gmail.com currently has no valid FB) | Blocks all Meta ad access — boss can't grant permissions until FB exists | Alishba |  | P0 | Not started | SeekhoAI_Requirements.docx — Req R1
T002 | 1. Foundation | Set up Meta Business Suite / Business Manager at business.facebook.com | You cannot run ads off a personal profile | Alishba | FB account | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Guide Phase 0
T003 | 1. Foundation | Create Facebook Business Page for SeekhoAI | Ads run from a Page, not a profile | Alishba | Business Manager | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Guide Phase 0
T004 | 1. Foundation | Connect Instagram account to the Page (if available) | Lets the same ad run on IG placements | Alishba | FB Business Page | P1 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Guide Phase 0
T005 | 1. Foundation | Create Ad Account inside Business Manager; set currency to PKR | All reporting must match local maths | Alishba | Business Manager | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Guide Phase 0
T006 | 1. Foundation | Add payment method (card) to the ad account | Without billing, Publish button fails | Alishba | Ad Account | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Guide Phase 0
T007 | 1. Foundation | Ask boss to grant FB access to the new account | Boss said he will grant once FB exists | Alishba ↔ Boss | FB account | P0 | Not started | WhatsApp messages 30–31 May 2026 — Boss msg 10:53 PM
T008 | 1. Foundation | Get WhatsApp business number from Maaz | Required for WhatsApp funnel + floating button + ads | Maaz → Alishba |  | P0 | Not started | SeekhoAI_Requirements.docx — Req R5
T009 | 1. Foundation | Get Easypaisa details from Maaz | Required for 999 PKR checkout close | Maaz → Alishba |  | P0 | Not started | SeekhoAI_Requirements.docx — Req R6
T010 | 1. Foundation | Find Stripe invite email in sa542 inbox; accept access | Boss already granted sa542; need to claim | Alishba |  | P0 | Not started | WhatsApp messages 30–31 May 2026 — Boss msg 10:35 PM
T011 | 2. Site blockers | Build real Privacy Policy page (replace # link) | Meta rejects ads without a privacy policy | Alishba + Maaz |  | P0 | Not started | SeekhoAI_Requirements.docx — Req C1 / Updates 2.1
T012 | 2. Site blockers | Build real Terms page (replace # link) | Compliance + trust | Alishba + Maaz |  | P0 | Not started | SeekhoAI_Requirements.docx — Req C1 / Updates 2.1
T013 | 2. Site blockers | Build real Refund page stating 30-day money-back guarantee | Consistency with on-page claim | Alishba + Maaz |  | P0 | Not started | SeekhoAI_Requirements.docx — Req C2 / Updates 2.1
T014 | 2. Site blockers | Remove fake testimonials (Sarah Chen, Michael Rodriguez, Jennifer Park, etc.) | American stock names signal scam to PK buyers — kills conversion | Alishba |  | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 2.2
T015 | 2. Site blockers | Collect 3–6 real Udemy review screenshots (incl. 2–3 local PK students) | The single biggest trust asset you have | Alishba |  | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 2.2 / F6
T016 | 2. Site blockers | Replace placeholder instructor portrait with real photo of Saad | Founder-led course with no founder photo wastes biggest trust asset | Alishba (asset) + Maaz |  | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 2.3 / F5
T017 | 2. Site blockers | Remove all USD pricing ($499, $1499) from the site | Single PKR offer — no contradictions | Maaz |  | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 2.5 / F8
T018 | 2. Site blockers | Remove MASTER80 code path (the 4999→999 IS the discount) | Three different prices today; cold visitor bounces | Maaz |  | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 2.5 / F8
T019 | 2. Site blockers | Lock single price sitewide: 4999 → 999 PKR (80% off) | One coherent offer everywhere | Maaz | Remove USD + MASTER80 | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 4 / F8
T020 | 3. Homepage revamp | F1 — Rebuild hero: headline + subhead + social-proof bar + ONE primary CTA + YT video, above fold | Mobile fold must show social proof | Maaz | Site blockers done | P0 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F1
T021 | 3. Homepage revamp | Drop in Part B hero copy verbatim ('PAKISTAN'S MOST-ENROLLED AI COURSE…') | Ship-ready copy from spec | Maaz | F1 | P0 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec Part B
T022 | 3. Homepage revamp | F2 — Add trust strip (Udemy + employer credibility) full-width below hero | Reinforces social proof above scroll | Maaz | F1 | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F2
T023 | 3. Homepage revamp | F3 — Move 'Who this is for' high (after trust strip) with 3 cards: Beginner / Professional / Founder | Self-qualifies visitor early | Maaz | F2 | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F3
T024 | 3. Homepage revamp | F4 — Merge old 10 pillars + 8 modules into ONE outcome-led section, 6 accordions | No duplicate content; detail in expandables | Maaz |  | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F4
T025 | 3. Homepage revamp | F5 — Instructor section with REAL photo | See blocker | Maaz | Real photo from boss | P0 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F5
T026 | 3. Homepage revamp | F6 — Replace ALL fake testimonials with real Udemy screenshots + 2–3 local students | See blocker | Maaz | Real screenshots | P0 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F6
T027 | 3. Homepage revamp | F7 — Free-course band as clearly-marked secondary CTA linking to /free | Distinct band so paid CTA stays primary | Maaz | /free page exists | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F7
T028 | 3. Homepage revamp | F8 — Single pricing block: 4999 → 999 PKR, JazzCash/Easypaisa, 30-day guarantee | No USD, no MASTER80 anywhere | Maaz | Site blockers done | P0 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F8
T029 | 3. Homepage revamp | F9 — Keep FAQ near bottom; update with 9 FAQs from Part B (PKR + cert + English-with-subtitles) | Don't claim Urdu — course is English with subtitles | Maaz |  | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F9
T030 | 3. Homepage revamp | F10 — Final CTA: repeat primary CTA + social-proof number | Single clean close | Maaz | F1 | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F10
T031 | 3. Homepage revamp | F11 — Remove top nav (or reduce to logo + one CTA button) | Every nav link is an exit | Maaz |  | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F11
T032 | 3. Homepage revamp | F12 — One consistent primary CTA ('Enrol Now — 999 PKR') repeated 3–4× sitewide | Same words, same colour, every time | Maaz | F8 | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F12
T033 | 3. Homepage revamp | F13 — Floating WhatsApp click-to-chat button (sticky, all viewports), wa.me with pre-filled text | Sticky entry to WhatsApp from anywhere on site | Maaz | WhatsApp number from Maaz | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec F13 / T6
T034 | 3. Homepage revamp | Use ONE stat set everywhere: 38,000+ students · 13,000+ reviews · 4.5★ · 100+ countries | Inconsistent numbers kill credibility | Maaz |  | P0 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec stat note
T035 | 4. /free page | Build new /free route — independent landing page for lead-capture ads only | Don't run ads to homepage; build dedicated page | Maaz |  | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 3 / Boss msg 6:55 PM
T036 | 4. /free page | Hero: ONE headline, ONE promise (e.g. 'Free 14-Hour GenAI Course — Start Today') | Concrete, not 'Master AI' | Maaz |  | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 3.1
T037 | 4. /free page | Signup form ABOVE the fold — Name, Email, Phone (WhatsApp) + consent checkbox + 'Get Free Access' button | Form must be the first thing visible | Maaz |  | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 3.1
T038 | 4. /free page | 'What you get' — 3–4 bullets covering 14h 33m, 179 lectures, 23 sections | Make the value of the free thing obvious | Maaz |  | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 3.1
T039 | 4. /free page | Proof section — real Udemy stats + 2–3 local reviews + screenshots + real instructor photo | No fake testimonials anywhere | Maaz | Real screenshots + photo | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 3.1
T040 | 4. /free page | Short instructor blurb (Deloitte / BMO / PwC, 38k+ students) | Single trust paragraph | Maaz |  | P1 | Not started | SeekhoAI_Website_Updates.docx — Updates 3.1
T041 | 4. /free page | Closing CTA button that scrolls back to the form | One offer, one action | Maaz |  | P1 | Not started | SeekhoAI_Website_Updates.docx — Updates 3.1
T042 | 4. /free page | REMOVE from /free: nav menu, pricing table, 10-pillar deep dive, any second offer | Every link is an exit; sale happens in WhatsApp | Maaz |  | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 3.2
T043 | 4. /free page | On submit: POST Name/Email/Phone to WhatsApp provider (or synced sheet) | Feeds the WhatsApp funnel | Maaz | WhatsApp provider chosen | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 3.3
T044 | 4. /free page | On submit: fire Meta Pixel 'Lead' event | Required for ad optimization | Maaz | Pixel installed | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 3.3 / T2
T045 | 4. /free page | On submit: trigger WhatsApp Message 0 (instant delivery) | Promise delivered instantly = trust | Maaz | WhatsApp provider wired | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 3.3 / Funnel M0
T046 | 4. /free page | Show 'Check your WhatsApp — your free course is on its way' confirmation | Closes the loop visually | Maaz |  | P1 | Not started | SeekhoAI_Website_Updates.docx — Updates 3.3
T047 | 5. Payments | Read Stripe email in sa542 inbox; understand what needs to happen end-to-end BEFORE writing code | Boss: $$$ involved — be cautious | Alishba | Stripe access claimed | P0 | Not started | WhatsApp messages 30–31 May 2026 — Boss msg 10:35 PM
T048 | 5. Payments | Build + test Stripe checkout in SANDBOX (test keys only) | Never touch prod first | Alishba + Maaz | Stripe sandbox | P0 | Not started | WhatsApp messages 30–31 May 2026 — Boss msg 10:35 PM
T049 | 5. Payments | Wire JazzCash payment link to the 999 PKR offer | Local wallets convert; cards don't at this price | Maaz | Easypaisa details | P0 | Not started | SeekhoAI_Requirements.docx — Req T5 / Updates 4
T050 | 5. Payments | Wire Easypaisa payment link to the 999 PKR offer | Local wallets convert; cards don't at this price | Maaz | Easypaisa details from Maaz | P0 | Not started | SeekhoAI_Requirements.docx — Req T5 / Updates 4
T051 | 5. Payments | Create Stripe production keys ONLY after sandbox is signed off | Boss offered to test live with small amount on his card | Alishba | Sandbox tested | P1 | Not started | WhatsApp messages 30–31 May 2026 — Boss msg 10:35 PM
T052 | 5. Payments | End-to-end test: enrol → pay → success page → receipt | Confirms full happy path | Alishba + Maaz | All payment rails | P0 | Not started
T053 | 6. Tracking | Create Meta Pixel in Events Manager → Connect Data Source → Web | One-time setup | Alishba | Business Manager | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Guide Phase 0 / R2
T054 | 6. Tracking | Give Maaz the pixel ID + install instructions; install sitewide | Pixel must load on every page | Alishba → Maaz | Pixel created | P0 | Not started | SeekhoAI_Requirements.docx — Req T1
T055 | 6. Tracking | Configure 'Lead' event to fire on free-course form submit | Most common beginner mistake to skip | Maaz | Pixel installed + /free form | P0 | Not started | SeekhoAI_Requirements.docx — Req T2 / Ads Phase 0
T056 | 6. Tracking | Configure 'Purchase' event to fire on successful payment | Required to track paid conversions | Maaz | Checkout wired | P0 | Not started | SeekhoAI_Requirements.docx — Req T3
T057 | 6. Tracking | Verify domain in Business Manager → Brand Safety → Domains | Required for iOS web-conversion tracking | Alishba | Business Manager | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 0
T058 | 6. Tracking | Configure Aggregated Event Measurement — rank 'Lead' as priority event | Makes iOS conversions track | Alishba | Pixel + Lead event | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 0
T059 | 6. Tracking | Install Google Analytics on the site (use sa542 account) | Pageviews + events tracked | Alishba + Maaz |  | P0 | Not started | SeekhoAI_Requirements.docx — Req R4 / T4
T060 | 6. Tracking | Verify with Meta Pixel Helper Chrome extension — submit test lead, confirm Lead event registers | Don't trust spend before this | Alishba | Everything above | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 3 step 20
T061 | 6. Tracking | Set up Meta MCP for posting + ad management from this environment | Lets Claude help run ads later | Alishba | FB access | P2 | Not started | SeekhoAI_Requirements.docx — Req R3
T062 | 7. WhatsApp funnel | Choose WhatsApp Business API provider (AiSensy / Wati / Interakt) | The free Business app cannot do automation at scale | Alishba + Maaz | WhatsApp number from Maaz | P0 | Not started | SeekhoAI_WhatsApp_Funnel.docx — Funnel 3.1
T063 | 7. WhatsApp funnel | Sign up + verify business number with chosen provider | Number must be API-registered | Alishba | Provider chosen | P0 | Not started | SeekhoAI_WhatsApp_Funnel.docx — Funnel 3.1
T064 | 7. WhatsApp funnel | Configure Message 0 (instant free-course delivery) as auto-reply on signup | Free-form, sent within 24h window | Alishba | Provider live | P0 | Not started | SeekhoAI_WhatsApp_Funnel.docx — Funnel M0
T065 | 7. WhatsApp funnel | Configure Message 1 (how to start) — sent 5–15 min after M0 | Activation + first proof point | Alishba | M0 | P0 | Not started | SeekhoAI_WhatsApp_Funnel.docx — Funnel M1
T066 | 7. WhatsApp funnel | Configure Message 2 (value tip + soft ask) — sent few hours later, still inside 24h | Get permission to pitch | Alishba | M1 | P0 | Not started | SeekhoAI_WhatsApp_Funnel.docx — Funnel M2
T067 | 7. WhatsApp funnel | Submit Message 3 (Day 2 — the 999 PKR offer) as APPROVED TEMPLATE | After 24h, only approved templates allowed | Alishba | Provider live | P0 | Not started | SeekhoAI_WhatsApp_Funnel.docx — Funnel M3
T068 | 7. WhatsApp funnel | Submit Message 4 (Day 3 — last call) as APPROVED TEMPLATE | Drives bulk of conversions in PK funnels | Alishba | Provider live | P0 | Not started | SeekhoAI_WhatsApp_Funnel.docx — Funnel M4
T069 | 7. WhatsApp funnel | Plan: handle first ~20–30 sales manually in WhatsApp; surface real objections | Don't automate the close before learning objections | Alishba |  | P1 | Not started | SeekhoAI_WhatsApp_Funnel.docx — Funnel 6
T070 | 8. Performance | LCP ≤ 2.5s on mobile 4G | Required perf target | Maaz |  | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec A5
T071 | 8. Performance | CLS < 0.1; INP < 200ms | Required perf target | Maaz |  | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec A5
T072 | 8. Performance | Google PageSpeed (mobile) ≥ 85 | Required perf target | Maaz |  | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec A5
T073 | 8. Performance | Lazy-load YouTube hero (facade) so it doesn't block LCP | Specific perf fix called out | Maaz |  | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec A5
T074 | 8. Performance | Compress images, convert to WebP, lazy-load below-fold | PK traffic is 90%+ mobile on 4G | Maaz |  | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec A5
T075 | 8. Performance | Test on a real mid-range Android over mobile data (not just desktop) | Where the actual audience is | Alishba | Site deployed | P1 | Not started | SeekhoAI_Homepage_Dev_Spec.docx — Dev Spec A5
T076 | 9. Deploy | Work with Maaz to deploy all site updates + /free page to production | Final deployment | Maaz + Alishba | Phases 2–8 done | P0 | Not started | SeekhoAI_Requirements.docx — Req R8 / Boss msg 7:31 PM
T077 | 9. Deploy | Smoke test full path on production: home → /free → submit → WhatsApp delivers → checkout → purchase event | One real signup before any ad spend | Alishba | Deploy done | P0 | Not started | SeekhoAI_Website_Updates.docx — Updates 5
T078 | 10. Ads launch | Produce 4 ad creatives to spec: 1:1 or 4:5 for feed, 9:16 for Stories/Reels; ≥1080×1080; hook in first 3s | Wrong dims = ads look broken on mobile | Alishba | Brand + assets | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 4
T079 | 10. Ads launch | In Ads Manager → Create → Objective: Leads | Locked objective | Alishba | Phase 9 done | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 1
T080 | 10. Ads launch | Name campaign: 'SeekhoAI – Free Course – Leads – Test 1' | Naming convention from spec | Alishba |  | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 1
T081 | 10. Ads launch | Leave Advantage campaign budget OFF; set budget at ad-set level | Control over spend | Alishba |  | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 1
T082 | 10. Ads launch | Ad set: Conversion location = Website (NOT Instant Form); Pixel + Lead event attached | Most common beginner mistake | Alishba | Pixel verified | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 2
T083 | 10. Ads launch | Daily budget 1,500–2,500 PKR; no end date | Discovery budget | Alishba |  | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 2
T084 | 10. Ads launch | Audience: Pakistan, age 18–40, language English, NO interests, all genders, Advantage+ placements | Broad on purpose — let pixel learn | Alishba |  | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 2
T085 | 10. Ads launch | ONE ad set, 3–4 ads inside it (don't split budget across multiple ad sets) | Splitting starves learning | Alishba |  | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 2
T086 | 10. Ads launch | Build Ad #1 — Aspiration / Earning hook (copy from Phase 5 of Ads Guide) | Hook variant 1 | Alishba | Creatives ready | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 5
T087 | 10. Ads launch | Build Ad #2 — Pain / FOMO hook | Hook variant 2 | Alishba | Creatives ready | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 5
T088 | 10. Ads launch | Build Ad #3 — Proof / Credibility hook | Hook variant 3 | Alishba | Creatives ready | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 5
T089 | 10. Ads launch | Build Ad #4 — Curiosity / Practical hook | Hook variant 4 | Alishba | Creatives ready | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 5
T090 | 10. Ads launch | On every ad verify: destination URL = /free, Lead event attached, CTA = 'Sign Up' / 'Learn More' | Catches the most common silent failures | Alishba | All 4 ads built | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 3
T091 | 10. Ads launch | Publish; wait for ad review (can take hours); confirm active | Standard Meta workflow | Alishba |  | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 3
T092 | 10. Ads launch | Submit one real test lead via Pixel Helper; confirm Lead event in Events Manager | Last gate before spend | Alishba |  | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 3
T093 | 10. Ads launch | DO NOT touch the campaign for 4–5 days (learning phase resets on any edit) | Single biggest waste of money | Alishba | Launched | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 3 / Phase 7
T094 | 11. Iterate | After 5 days: compute CPL, lead-to-sale %, CPB, profit/sale | These are the 4 numbers everything else hinges on | Alishba | Learning phase done | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 6
T095 | 11. Iterate | Kill any ad that spent ~2× target CPL with zero leads | Stop the bleed | Alishba | Day 5+ | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 7
T096 | 11. Iterate | Keep + scale the ad with lowest CPL + highest CTR — change ONE variable at a time | Discipline beats cleverness | Alishba | Day 5+ | P0 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 7
T097 | 11. Iterate | Scale winning ad budget by 20–30% every few days (big jumps reset learning) | Compounds toward $1,000 | Alishba | Winner identified | P1 | Not started | SeekhoAI_Meta_Ads_Launch_Guide.docx — Ads Phase 7
T098 | 12. Tracker | Upload this XLSX to Excel Online / OneDrive; share edit link with boss | Boss specifically asked for Excel Online with edit access | Alishba |  | P0 | Not started | SeekhoAI_Requirements.docx — Req R9 / Boss msg 10:55 PM
T099 | 12. Tracker | Update Status column daily; review with boss weekly | Keeps boss in the loop without daily check-ins | Alishba | Tracker shared | P1 | Not started | SeekhoAI_Requirements.docx — Req R9

## How to use
SeekhoAI Task Tracker — How to use
Built from the 5 docs the boss sent on 31 May 2026:
• SeekhoAI_Requirements.docx
• SeekhoAI_Homepage_Dev_Spec.docx
• SeekhoAI_Website_Updates.docx
• SeekhoAI_WhatsApp_Funnel.docx
• SeekhoAI_Meta_Ads_Launch_Guide.docx
Columns:
ID — stable task id (T001…). Use to reference in chat/email.
Phase — sequence group. Do phases in order; tasks inside a phase can often run in parallel.
Task — what to do.
Why — the reason it exists; don't drop it without checking the why.
Owner — Alishba / Maaz / both / Boss.
Depends on — what must be done before you can start.
Priority — P0 = blocker, P1 = important, P2 = nice-to-have.
Status — update to: Not started / In progress / Blocked / Done.
Source doc — exact reference back to the boss's docs.
Notes — your working notes / questions / links.
Phase order (the critical path):
1. Foundation — accounts, access, inputs from Maaz
2. Site blockers — legal pages, fake testimonials, fake photo, USD/MASTER80 pricing
3. Homepage revamp — F1–F13 + Part B copy from the dev spec
4. /free page — the new ad-only landing page
5. Payments — Stripe sandbox → JazzCash/Easypaisa → Stripe prod
6. Tracking — Pixel, GA, Lead/Purchase events, domain verify
7. WhatsApp funnel — provider + 5-message sequence (M3 & M4 are templates)
8. Performance — LCP, CLS, PageSpeed, mobile 4G test
9. Deploy — Maaz + smoke test full path
10. Ads launch — One campaign, one ad set, 4 ads, then DO NOT TOUCH for 4–5 days
11. Iterate — CPL → lead-to-sale % → CPB → scale winner
12. Tracker — Excel Online upload + boss share
Hard rules from the boss / docs:
• Don't claim the course is 'in Urdu'. It is English with subtitles.
• Single pricing block sitewide: 4999 → 999 PKR. No USD. No MASTER80.
• One stat set everywhere: 38,000+ students · 13,000+ reviews · 4.5★ · 100+ countries.
• Stripe: build in sandbox first. Real money — go slow.
• Ads: conversion = Website (not Instant Form). Lead event MUST be attached.
• After ads launch, do not touch campaign for 4–5 days (learning phase).
• WhatsApp 24-hour rule: messages 0–2 free-form, messages 3–4 must be approved templates.
• Don't run ads to the homepage — only to /free.

## KPIs
Metric | Target / Formula | Current | Notes
LCP (mobile 4G) | ≤ 2.5 s |  | Dev Spec A5
Full page load | ≤ 3 s |  | Dev Spec A5
CLS | < 0.1 |  | Dev Spec A5
INP | < 200 ms |  | Dev Spec A5
Google PageSpeed (mobile) | ≥ 85 |  | Dev Spec A5
CPL (cost per lead) | ad spend ÷ signups |  | Ads Phase 6 — low tens of PKR healthy
CTR | > 1% healthy / < 0.7% weak |  | Ads Phase 6
Lead → sale % | signups → buyers |  | Discover; do not assume
CPB (cost per buyer) | CPL ÷ lead-to-sale % |  | Ads Phase 6
Profit per sale | 999 PKR − CPB |  | Ads Phase 6
Revenue target | $1,000 ≈ 285 sales |  | Volume game, 6–10 wk realistic